## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Owner | To Create a Business Promotion Plan | I can promote my product to right people
1 | SB1/US2 | Owner | To See The Research and Development Plan of My Company | I Can Start Promoting the Product
1 | SB1/US3 | Owner | Target Audience Attestation | I Can See My Business Working
1 | SB1/US4 | Owner | To Create the SMM Promotion Plan | I Can See My Business Working
1 | SB1/US5 | Owner | Creation of Content | I Can Start Promoting the Product
1 | SB1/US6 | Owner | Create or Opening the Raw Project | I can start make video
1 | SB1/US7 | Owner | Import Object | I Can Participate in the Functions
1 | SB1/US8 | Owner | Sound Effects | I can add sound effect in video
1 | SB1/US9 | Owner | Video Voiceover | I can add voiceover in promotion video
1 | SB1/US10 | Owner | Video After Effect Project | I can add after effects in promotion
1 | SB1/US11 | Owner | Video Animation | I can have a good video
1 | SB1/US12 | Owner | Text Font Selection for Video | I can have a effective video
1 | SB1/US13 | Owner | Character Design in Video | I can easily influence audience
1 | SB1/US14 | Owner | Video Precomposing | I can make a good video
1 | SB1/US15 | Owner | Clubbing of Text and Animation in Video | I can make a good video
1 | SB1/US16 | Owner | Video Sequencing | I can make a good video
1 | SB1/US17 | Owner | Motion Graphing | I can make a good video
1 | SB1/US18 | Owner | Keying | I can make a good video
1 | SB1/US19 | Owner | Video Quality | I can have the video in deifferent qualities
1 | SB1/US20 | Owner | Video Rendering | I can complete the video making process
2 | SB2/US1 | Owner | Design Logo | I can have a particular logo to advertise or promotion
2 | SB2/US2 | Owner | To Create the SMO Promotion Plan | I have a pre planning to complete the process
2 | SB2/US3 | Owner | Creation of Business Account on Gmail | I can connect all the activities with the gmail account
2 | SB2/US4 | Owner | Creation of Business Account on Social Media Paltforms | I Can Start Promoting the Product on social media
2 | SB2/US5 | Owner | Create Brochures | I can influence the people in efficient way
2 | SB2/US6 | Owner | Blogging | I can touch the positive issues of the product
2 | SB2/US7 | Owner | Clubbing of SMO and SMM | I can take the promotion to next level
2 | SB2/US8 | Owner | Set Crieterion of Target Audience | Promotion reach to all the interested audience
2 | SB2/US9 | Owner | Promotion on Facebook | I can connect with audience in better way
2 | SB2/US10 | Owner | Promotion on Instagram | I can connect with audience in better way
2 | SB2/US11 | Owner | Promotion on Twitter | I can connect with audience in better way
2 | SB2/US12 | Owner | Promotion on Telegram | I can connect with audience in better way
2 | SB2/US13 | Owner | Promotion on Reddit | I can connect with audience in better way
2 | SB2/US14 | Owner | Promotion on LinkedIn | I can connect with audience in better way
2 | SB2/US15 | Owner | Promotion on Youtube | I can connect with audience in better way
2 | SB2/US16 | Owner | Promotion of Logo | I can marketing the product in easy way
2 | SB2/US17 | Owner | Publishing Tools | I can easily use video for promotion
2 | SB2/US18 | Owner | Demographics | I can make a good effect on audience
3 | SB3/US1 | Owner | Sponsored Advertisement | I can advertise the product on paid basis
3 | SB3/US2 | Owner | Feedback | I can know the interest of the audience
3 | SB3/US3 | Owner | Edit the Content for the Best Audience Output | I can influence more and more aduience for product
3 | SB3/US4 | Owner | To Create the SEO Promotion Plan | Website or product become more popular
3 | SB3/US5 | Owner | Google Keyword Planner | I can buy the paid keywords
3 | SB3/US6 | Owner | Select Most Relevant Keyword | Product will serve on the top
3 | SB3/US7 | Owner | Bidding for Keyword | I can buy good keyword for promotion
3 | SB3/US8 | Owner | Edit Blogs | I can add keyword in it
3 | SB3/US9 | Owner | Edit Website | I can add keyword in it
3 | SB3/US10 | Owner | Edit Advertisement and Posts | I can add keyword in it
3 | SB3/US11 | Owner | Reddit Commenting | I can add keyword in it
3 | SB3/US12 | Owner | Creating the Best Marginal Utility Function | More audience will effect
3 | SB3/US13 | Owner | Checking the Brochures and Editing | I can add keyword in it
3 | SB3/US14 | Owner | Increase Traffic on Website | Website is opens several in order to come in topm results
3 | SB3/US15 | Owner | Show Response through Google Analytics | I can show reviews
3 | SB3/US16 | Owner | Show Response through Facebook Analytics (post traffic) | I can show reviews
3 | SB3/US17 | Owner | Show Hyperstat (website traffic) | I can show reviews
3 | SB3/US18 | Owner | Tying Up | I can show reviews
4 | SB4/US1 | Owner | Add D-DOS Code in Website | Website can handle traffic
4 | SB4/US2 | Owner | Circulate Website Traffic | If more traffic comes on website it handles that
4 | SB4/US3 | Owner | Maintain the Traffic | If more traffic comes on website it handles that
4 | SB4/US4 | Owner | Keep on Creation of Post | Promotion Continues
4 | SB4/US5 | Owner | Make New Posts and Advertisement on Social Media | Promotion Continues
4 | SB4/US6 | Owner | Make Bid on New Keyword | I can buy new keywords
4 | SB4/US7 | Owner | Maintain Website with New Bidding Keywords | To tale websites and posts to maximum
4 | SB4/US8 | Owner | Make and Post New Blogs | Promotion Continues
4 | SB4/US9 | Owner | Design New Brochures according to need | Promotion Continues
4 | SB4/US10 | Owner | Maintain the Daily Update through Website | Promotion Continues

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Digital College>
SB1/US1 | To Create a Business Promotion Plan | SB1/D1/T1 | product awareness | SG | Not Start
|  | SB1/D1/T2 | requirement understanding | SG | Not Start
|  | SB1/D1/T3 | name selection | SG | Not Start
|  | SB1/D1/T4 | marketing strategy making | SG | Not Start
SB1/US2 | To See The Research and Development Plan of My Company | SB1/D2/T1 | demographics | PV | Not Start
|  | SB1/D2/T2 | age of audience | PV | Not Start
|  | SB1/D2/T3 | language and type of audience | PV | Not Start
|  | SB1/D2/T4 | content that should go in the crowd | PV | Not Start
SB1/US3 | Target Audience Attestation | SB1/D3/T1 | demographics | PV | Not Start
|  | SB1/D3/T2 | age of audience | PV | Not Start
|  | SB1/D3/T3 | language and type | PV | Not Start
SB1/US4 | To Create the SMM Promotion Plan | SB1/D4/T1 | creation of the layers of apps that will be used | SS | Not Start
|  | SB1/D4/T2 | creation of posts and writings | SS | Not Start
|  | SB1/D4/T3 | creation videos | SS | Not Start
|  | SB1/D4/T4 | creation of page | PV | Not Start
SB1/US5 | Creation of Content | SB1/D5/T1 | topic knowledge | PV | Not Start
|  | SB1/D5/T2 | current issue with some humor | PV | Not Start
|  | SB1/D5/T3 | write your knowledge | PV | Not Start
SB1/US6 | Create or Opening the Raw Project | SB1/D6/T1 | open the after effects | PV | Not Start
|  | SB1/D6/T2 | select the fps and quality of the video | PV | Not Start
|  | SB1/D6/T3 | start the process | PV | Not Start
SB1/US7 | Import Object | SB1/D7/T2 | add png | SS | Not Start
|  | SB1/D7/T3 | add jpg | SS | Not Start
|  | SB1/D7/T4 | add mkv file into your projects | SS | Not Start
SB1/US8 | Sound Effects | SB1/D8/T1 | import voiceover | PV | Not Start
|  | SB1/D8/T2 | import lyrical | PV | Not Start
|  | SB1/D8/T3 | import the wave music file for any video | SG | Not Start
SB1/US9 | Video Voiceover | SB1/D9/T1 | content writing | SG | Not Start
|  | SB1/D9/T2 | studio recording | SG | Not Start
|  | SB1/D9/T3 | balancing the voice | SG | Not Start
SB1/US10 | Video After Effect Project | SB1/D10/T1 | create content | SG | Not Start
|  | SB1/D10/T2 | add layerings | SG | Not Start
|  | SB1/D10/T3 | add objects and sound | SG | Not Start
|  | SB1/D10/T4 | and make a video | SG | Not Start
SB1/US11 | Video Animation | SB1/D11/T2 | create content | SG | Not Start
|  | SB1/D11/T3 | add layerings | SG | Not Start
|  | SB1/D11/T4 | add objects and sound | SG | Not Start
|  | SB1/D11/T5 | and make a video | SG | Not Start
SB1/US12 | Text Font Selection for Video | SB1/D12/T1 | software function | SS | Not Start
SB1/US13 | Character Design in Video | SB1/D13/T1 | illustrator design and techniques | SG | Not Start
SB1/US14 | Video Precomposing | SB1/D14/T1 | selection of all objects and renaming them | SG | Not Start
|  | SB1/D14/T2 | clubbing them | SG | Not Start
|  | SB1/D14/T3 | and precompose them into on epacket | SG | Not Start
SB1/US15 | Clubbing of Text and Animation in Video | SB1/D15/T2 | import video in AE | SG | Not Start
|  | SB1/D15/T3 | import voiceover in AE | SG | Not Start
SB1/US16 | Video Sequencing | SB1/D16/T1 | with the splitting and arrangements match the dubbing | SG | Not Start
|  | SB1/D16/T2 | after recomposition | SG | Not Start
|  | SB1/D16/T3 | arranging video in time vise | SG | Not Start
SB1/US17 | Motion Graphing | SB1/D17/T1 | keying | SG | Not Start
|  | SB1/D17/T2 | moulding | SG | Not Start
|  | SB1/D17/T3 | transitions | SG | Not Start
SB1/US18 | Keying | SB1/D18/T1 | removing any object | SG | Not Start
|  | SB1/D18/T2 | removing any color | SG | Not Start
|  | SB1/D18/T3 | connecting the object with certain motion changes | SG | Not Start
|  | SB1/D18/T4 | quicktime | SG | Not Start
SB1/US19 | Video Quality | SB1/D19/T1 | mkv | PV | Not Start
|  | SB1/D19/T2 | avi | PV | Not Start
|  | SB1/D19/T3 | lossless | PV | Not Start
SB1/US20 | Video Rendering | SB1/D20/T1 | select quality | PV | Not Start
|  | SB1/D20/T2 | select format | PV | Not Start
PV - PRATEEK VASHISHTHA
SG - SHAKTI GOKHRU
SS - SHYAM SINGH

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | TM | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | To Create a Business Promotion Plan | product awareness | SG | Not Start | 5
|  | requirement understanding | SG | Not Start | 5
|  | name selection | SG | Not Start | 5
|  | marketing strategy making | SG | Not Start | 5
2 | To See The Research and Development Plan of My Company | demographics | PV | Not Start | 5
|  | age of audience | PV | Not Start | 5
|  | language and type of audience | PV | Not Start | 5
|  | content that should go in the crowd | PV | Not Start | 5
3 | Target Audience Attestation | demographics | PV | Not Start | 5
|  | age of audience | PV | Not Start | 5
|  | language and type | PV | Not Start | 5
4 | To Create the SMM Promotion Plan | creation of the layers of apps that will be used | SS | Not Start | 5
|  | creation of posts and writings | SS | Not Start | 5
|  | creation videos | SS | Not Start | 5
|  | creation of page | PV | Not Start | 5
5 | Creation of Content | topic knowledge | PV | Not Start | 5
|  | current issue with some humor | PV | Not Start | 5
|  | write your knowledge | PV | Not Start | 5
6 | Create or Opening the Raw Project | open the after effects | PV | Not Start | 5
|  | select the fps and quality of the video | PV | Not Start | 5
|  | start the process | PV | Not Start | 5
7 | Import Object | add png | SS | Not Start | 5
|  | add jpg | SS | Not Start | 5
|  | add mkv file into your projects | SS | Not Start | 5
8 | Sound Effects | import voiceover | PV | Not Start | 5
|  | import lyrical | PV | Not Start | 5
|  | import the wave music file for any video | SG | Not Start | 5
9 | Video Voiceover | content writing | SG | Not Start | 5
|  | studio recording | SG | Not Start | 5
|  | balancing the voice | SG | Not Start | 5
10 | Video After Effect Project | create content | SG | Not Start | 5
|  | add layerings | SG | Not Start | 5
|  | add objects and sound | SG | Not Start | 5
|  | and make a video | SG | Not Start | 5
11 | Video Animation | create content | SG | Not Start | 5
|  | add layerings | SG | Not Start | 5
|  | add objects and sound | SG | Not Start | 5
|  | and make a video | SG | Not Start | 5
12 | Text Font Selection for Video | software function | SS | Not Start | 5
13 | Character Design in Video | illustrator design and techniques | SG | Not Start | 5
14 | Video Precomposing | selection of all objects and renaming them | SG | Not Start | 5
|  | clubbing them | SG | Not Start | 5
|  | and precompose them into on epacket | SG | Not Start | 5
15 | Clubbing of Text and Animation in Video | import video in AE | SG | Not Start | 5
|  | import voiceover in AE | SG | Not Start | 5
16 | Video Sequencing | with the splitting and arrangements match the dubbing | SG | Not Start | 5
|  | after recomposition | SG | Not Start | 5
|  | arranging video in time vise | SG | Not Start | 5
17 | Motion Graphing | keying | SG | Not Start | 5
|  | moulding | SG | Not Start | 5
|  | transitions | SG | Not Start | 5
18 | Keying | removing any object | SG | Not Start | 5
|  | removing any color | SG | Not Start | 5
|  | connecting the object with certain motion changes | SG | Not Start | 5
|  | quicktime | SG | Not Start | 5
19 | Video Quality | mkv | PV | Not Start | 5
|  | avi | PV | Not Start | 5
|  | lossless | PV | Not Start | 5
20 | Video Rendering | select quality | PV | Not Start | 5
|  | select format | PV | Not Start | 5
PV - PRATEEK VASHISHTHA
SG - SHAKTI GOKHRU
SS - SHYAM SINGH

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 60 | 60 | Tasks
2018-09-12 | 50 | 60
2018-09-11 | 40 | 60
2018-09-14 | 30 | 60
2018-09-16 | 20 | 60
2018-09-18 | 10 | 60
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Digital College>
SB2/US1 | Design Logo | SB2/D1/T1 | product awareness | SG | NOT STARTED
|  | SB2/D1/T2 | create descriptions logo | SG | NOT STARTED
|  | SB2/D1/T3 | name selection | SG | NOT STARTED
SB2/US2 | To Create the SMO Promotion Plan | SB2/D2/T1 | demographics | SS | NOT STARTED
|  | SB2/D2/T2 | age of audience | SS | NOT STARTED
|  | SB2/D2/T3 | language and type of audience | SS | NOT STARTED
|  | SB2/D2/T4 | content that should go in the crowd | SS | NOT STARTED
SB2/US3 | Creation of Business Account on Gmail | SB2/D3/T1 | create the gmail account | PV | NOT STARTED
|  | SB2/D3/T2 | connect all social media account with gmail | PV | NOT STARTED
SB2/US4 | Creation of Business Account on Social Media Paltforms | SB2/D4/T1 | create business pages | PV | NOT STARTED
|  | SB2/D4/T2 | dont add personal details of yours | PV | NOT STARTED
|  | SB2/D4/T3 | or any pic , name the name as the companies name | PV | NOT STARTED
SB2/US5 | Create Brochures | SB2/D5/T1 | topic knowledge | SG | NOT STARTED
|  | SB2/D5/T2 | current issue with some humor | SG | NOT STARTED
|  | SB2/D5/T3 | write your knowledge | SG | NOT STARTED
|  | SB2/D5/T4 | and create the image | SG | NOT STARTED
SB2/US6 | Blogging | SB2/D6/T1 | topic knowledge | PV | NOT STARTED
|  | SB2/D6/T2 | current issue with some humor | PV | NOT STARTED
|  | SB2/D6/T3 | write your knowledge | PV | NOT STARTED
SB2/US7 | Clubbing of SMO and SMM | SB2/D7/T2 | creation of the layers of apps that will be used | SS | NOT STARTED
|  | SB2/D7/T3 | creation of posts and writings | SS | NOT STARTED
|  | SB2/D7/T4 | creation videos | SS | NOT STARTED
|  | SB2/D7/T5 | creation of page | SS | NOT STARTED
|  | SB2/D8/T1 | creation of the layers of apps that will be used | SS | NOT STARTED
SB2/US8 | Set Crieterion of Target Audience | SB2/D8/T2 | topic knowledge | SS | NOT STARTED
|  | SB2/D8/T3 | current issue with some humor | SS | NOT STARTED
|  | SB2/D8/T4 | write your knowledge | SS | NOT STARTED
|  | SB2/D9/T1 | topic knowledge | SS | NOT STARTED
SB2/US9 | Promotion on Facebook | SB2/D9/T2 | publishing tools | PV | NOT STARTED
|  | SB2/D9/T3 | demographics | PV | NOT STARTED
|  | SB2/D9/T4 | age of audience | PV | NOT STARTED
|  | SB2/D9/T5 | type of content flowing | PV | NOT STARTED
SB2/US10 | Promotion on Instagram | SB2/D10/T1 | publishing tools | PV | NOT STARTED
|  | SB2/D10/T2 | demographics | PV | NOT STARTED
|  | SB2/D10/T3 | age of audience | PV | NOT STARTED
|  | SB2/D10/T4 | type of content flowing | PV | NOT STARTED
SB2/US11 | Promotion on Twitter | SB2/D10/T5 | publishing tools | PV | NOT STARTED
|  | SB2/D11/T2 | demographics | PV | NOT STARTED
|  | SB2/D11/T3 | age of audience | PV | NOT STARTED
|  | SB2/D11/T4 | type of content flowing | PV | NOT STARTED
SB2/US12 | Promotion on Telegram | SB2/D11/T5 | publishing tools | PV | NOT STARTED
|  | SB2/D12/T1 | demographics | PV | NOT STARTED
|  | SB2/D12/T2 | age of audience | PV | NOT STARTED
|  | SB2/D12/T3 | type of content flowing | PV | NOT STARTED
SB2/US13 | Promotion on Reddit | SB2/D13/T1 | publishing tools | PV | NOT STARTED
|  | SB2/D13/T2 | demographics | PV | NOT STARTED
|  | SB2/D13/T3 | age of audience | PV | NOT STARTED
|  | SB2/D13/T4 | type of content flowing | PV | NOT STARTED
SB2/US14 | Promotion on LinkedIn | SB2/D14/T1 | publishing tools | PV | NOT STARTED
|  | SB2/D14/T2 | demographics | PV | NOT STARTED
|  | SB2/D14/T3 | age of audience | PV | NOT STARTED
|  | SB2/D14/T4 | type of content flowing | PV | NOT STARTED
SB2/US15 | Promotion on Youtube | SB2/D15/T2 | publishing tools | SS | NOT STARTED
|  | SB2/D15/T3 | demographics | SS | NOT STARTED
|  | SB2/D15/T4 | age of audience | SS | NOT STARTED
|  | SB2/D15/T5 | type of content flowing | SS | NOT STARTED
SB2/US16 | Promotion of Logo | SB2/D16/T1 |  | SG | NOT STARTED
SB2/US17 | Publishing Tools | SB2/D17/T1 | import video in AE | SS | NOT STARTED
|  | SB2/D17/T2 | import voiceover in AE | SS | NOT STARTED
|  | SB2/D17/T3 | after recomposition | SS | NOT STARTED
|  | SB2/D17/T4 | arranging video in time vise | SS | NOT STARTED
SB2/US18 | Demographics | SB2/D18/T1 | transitions | SS | NOT STARTED
|  | SB2/D18/T2 | keying | SS | NOT STARTED
|  | SB2/D18/T3 | moulding | SS | NOT STARTED
PV - PRATEEK VASHISHTHA
SG - SHAKTI GOKHRU
SS - SHYAM SINGH

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Design Logo | product awareness | SG | NOT STARTED | 5
|  | create descriptions logo | SG | NOT STARTED | 5
|  | name selection | SG | NOT STARTED | 5
2 | To Create the SMO Promotion Plan | demographics | SS | NOT STARTED | 5
|  | age of audience | SS | NOT STARTED | 5
|  | language and type of audience | SS | NOT STARTED | 5
|  | content that should go in the crowd | SS | NOT STARTED | 5
3 | Creation of Business Account on Gmail | create the gmail account | PV | NOT STARTED | 5
|  | connect all social media account with gmail | PV | NOT STARTED | 5
4 | Creation of Business Account on Social Media Paltforms | create business pages | PV | NOT STARTED | 5
|  | dont add personal details of yours | PV | NOT STARTED | 5
|  | or any pic , name the name as the companies name | PV | NOT STARTED | 5
5 | Create Brochures | topic knowledge | SG | NOT STARTED | 5
|  | current issue with some humor | SG | NOT STARTED | 5
|  | write your knowledge | SG | NOT STARTED | 5
|  | and create the image | SG | NOT STARTED | 5
6 | Blogging | topic knowledge | PV | NOT STARTED | 5
|  | current issue with some humor | PV | NOT STARTED | 5
|  | write your knowledge | PV | NOT STARTED | 5
7 | Clubbing of SMO and SMM | creation of the layers of apps that will be used | SS | NOT STARTED | 5
|  | creation of posts and writings | SS | NOT STARTED | 5
|  | creation videos | SS | NOT STARTED | 5
|  | creation of page | SS | NOT STARTED | 5
|  | creation of the layers of apps that will be used | SS | NOT STARTED | 5
8 | Set Crieterion of Target Audience | topic knowledge | PV | NOT STARTED | 5
|  | current issue with some humor | PV | NOT STARTED | 5
|  | write your knowledge | PV | NOT STARTED | 5
|  | topic knowledge | PV | NOT STARTED | 5
9 | Promotion on Facebook | publishing tools | PV | NOT STARTED | 5
|  | demographics | PV | NOT STARTED | 5
|  | age of audience | PV | NOT STARTED | 5
|  | type of content flowing | PV | NOT STARTED | 5
10 | Promotion on Instagram | publishing tools | PV | NOT STARTED | 5
|  | demographics | PV | NOT STARTED | 5
|  | age of audience | PV | NOT STARTED | 5
|  | type of content flowing | PV | NOT STARTED | 5
11 | Promotion on Twitter | publishing tools | PV | NOT STARTED | 5
|  | demographics | PV | NOT STARTED | 5
|  | age of audience | PV | NOT STARTED | 5
|  | type of content flowing | PV | NOT STARTED | 5
12 | Promotion on Telegram | publishing tools | PV | NOT STARTED | 5
|  | demographics | PV | NOT STARTED | 5
|  | age of audience | PV | NOT STARTED | 5
|  | type of content flowing | PV | NOT STARTED | 5
13 | Promotion on Reddit | publishing tools | PV | NOT STARTED | 5
|  | demographics | PV | NOT STARTED | 5
|  | age of audience | PV | NOT STARTED | 5
|  | type of content flowing | PV | NOT STARTED | 5
14 | Promotion on LinkedIn | publishing tools | PV | NOT STARTED | 5
|  | demographics | PV | NOT STARTED | 5
|  | age of audience | PV | NOT STARTED | 5
|  | type of content flowing | PV | NOT STARTED | 5
15 | Promotion on Youtube | publishing tools | SS | NOT STARTED | 5
|  | demographics | SS | NOT STARTED | 5
|  | age of audience | SS | NOT STARTED | 5
|  | type of content flowing | SS | NOT STARTED | 5
16 | Promotion of Logo |  | SG | NOT STARTED | 5
17 | Publishing Tools | import video in AE | SS | NOT STARTED | 5
|  | import voiceover in AE | SS | NOT STARTED | 5
|  | after recomposition | SS | NOT STARTED | 5
|  | arranging video in time vise | SS | NOT STARTED | 5
18 | Demographics | transitions | SS | NOT STARTED | 5
|  | keying | SS | NOT STARTED | 5
|  | moulding | SS | NOT STARTED | 5
PV - PRATEEK VASHISHTHA
SG - SHAKTI GOKHRU
SS - SHYAM SINGH

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 64 | 64 | Tasks
2017-09-28 | 50 | 64
2017-10-02 | 40 | 64
2017-10-05 | 30 | 64
2017-10-07 | 20 | 64
2017-10-09 | 5 | 64
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Digital College>
SB3/US1 | Sponsored Advertisement | SB3/D1/T1 | product awareness | SG | NOT STARTED
|  | SB3/D1/T2 | ad creation | SG | NOT STARTED
|  | SB3/D1/T3 | publish it | SG | NOT STARTED
SB3/US2 | Feedback | SB3/D2/T1 | google analytics | PV | NOT STARTED
|  | SB3/D2/T2 | hypestat | PV | NOT STARTED
|  | SB3/D2/T3 | alexa | PV | NOT STARTED
SB3/US3 | Edit the Content for the Best Audience Output | SB3/D3/T1 | use demography | SG | NOT STARTED
|  | SB3/D3/T2 | use age criterion and response on the content | SG | NOT STARTED
|  | SB3/D3/T3 | and edit the promotion | PV | NOT STARTED
SB3/US4 | To Create the SEO Promotion Plan | SB3/D4/T1 | topic knowledge | PV | NOT STARTED
|  | SB3/D4/T2 | current issue with some humor | PV | NOT STARTED
|  | SB3/D4/T3 | write your knowledge | PV | NOT STARTED
|  | SB3/D4/T4 | and create the image | PV | NOT STARTED
SB3/US5 | Google Keyword Planner | SB3/D5/T1 | basic knowledge | PV | NOT STARTED
|  | SB3/D5/T2 | bid the best character suited | PV | NOT STARTED
|  | SB3/D5/T3 | from google keywords planner | PV | NOT STARTED
|  | SB3/D5/T4 | and buy that | PV | NOT STARTED
SB3/US6 | Select Most Relevant Keyword | SB3/D6/T1 | topic knowledge | PV | NOT STARTED
|  | SB3/D6/T2 | current issue with some humor | PV | NOT STARTED
|  | SB3/D6/T3 | write your knowledge | PV | NOT STARTED
|  | SB3/D6/T4 | blogging will help too | PV | NOT STARTED
SB3/US7 | Bidding for Keyword | SB3/D7/T1 | go to GKP | PV | NOT STARTED
|  | SB3/D7/T2 | select your zone of marketing | PV | NOT STARTED
|  | SB3/D7/T3 | show u the keywords best for u | PV | NOT STARTED
|  | SB3/D7/T4 | quote the rate for them | PV | NOT STARTED
SB3/US8 | Edit Blogs | SB3/D8/T1 | topic knowledge | PV | NOT STARTED
|  | SB3/D8/T2 | current issue with some humor | PV | NOT STARTED
|  | SB3/D8/T3 | write your knowledge | PV | NOT STARTED
SB3/US9 | Edit Website | SB3/D9/T1 | topic knowledge | PV | NOT STARTED
|  | SB3/D9/T2 | current issue with some humor | PV | NOT STARTED
|  | SB3/D9/T3 | write your knowledge | PV | NOT STARTED
SB3/US10 | Edit Advertisement and Posts | SB3/D10/T1 | topic knowledge | PV | NOT STARTED
|  | SB3/D10/T2 | current issue with some humor | PV | NOT STARTED
|  | SB3/D10/T3 | write your knowledge | PV | NOT STARTED
|  | SB3/D10/T4 | type of content flowing | PV | NOT STARTED
SB3/US11 | Reddit Commenting | SB3/D11/T1 | choose and set best suitable time for reddit commenting | PV | NOT STARTED
|  | SB3/D11/T2 | use bought keyword during replying of comments | PV | NOT STARTED
SB3/US12 | Creating the Best Marginal Utility Function | SB3/D12/T1 | topic knowledge | PV | NOT STARTED
|  | SB3/D12/T2 | current issue with some humor | PV | NOT STARTED
|  | SB3/D12/T3 | give the audience what they are craving for | PV | NOT STARTED
SB3/US13 | Checking the Brochures and Editing | SB3/D13/T1 | publishing tools | SS | NOT STARTED
|  | SB3/D13/T2 | demographics | SS | NOT STARTED
|  | SB3/D13/T3 | age of audience | SS | NOT STARTED
|  | SB3/D13/T4 | type of content flowing | SS | NOT STARTED
SB3/US14 | Increase Traffic on Website | SB3/D14/T1 | seo | SS | NOT STARTED
|  | SB3/D14/T2 | blogging | SS | NOT STARTED
|  | SB3/D14/T3 | posting | SS | NOT STARTED
SB3/US15 | Show Response through Google Analytics | SB3/D15/T1 | reviewing | SG | NOT STARTED
|  | SB3/D15/T2 | showing | SG | NOT STARTED
SB3/US16 | Show Response through Facebook Analytics (post traffic) | SB3/D16/T1 | reviewing | SG | NOT STARTED
|  | SB3/D16/T2 | showing | SG | NOT STARTED
SB3/US17 | Show Hyperstat (website traffic) | SB3/D17/T1 | reviewing | SG | NOT STARTED
|  | SB3/D17/T2 | showing | SG | NOT STARTED
SB3/US18 | Tying Up | SB3/D18/T1 |  | SG | NOT STARTED
PV - PRATEEK VASHISHTHA
SG - SHAKTI GOKHRU
SS - SHYAM SINGH

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Sponsored Advertisement | product awareness | SG | NOT STARTED | 5
|  | ad creation | SG | NOT STARTED | 5
|  | publish it | SG | NOT STARTED | 5
2 | Feedback | google analytics | PV | NOT STARTED | 5
|  | hypestat | PV | NOT STARTED | 5
|  | alexa | PV | NOT STARTED | 5
3 | Edit the Content for the Best Audience Output | use demography | SG | NOT STARTED | 5
|  | use age criterion and response on the content | SG | NOT STARTED | 5
|  | and edit the promotion | PV | NOT STARTED | 5
4 | To Create the SEO Promotion Plan | topic knowledge | PV | NOT STARTED | 5
|  | current issue with some humor | PV | NOT STARTED | 5
|  | write your knowledge | PV | NOT STARTED | 5
|  | and create the image | PV | NOT STARTED | 5
5 | Google Keyword Planner | basic knowledge | PV | NOT STARTED | 5
|  | bid the best character suited | PV | NOT STARTED | 5
|  | from google keywords planner | PV | NOT STARTED | 5
|  | and buy that | PV | NOT STARTED | 5
6 | Select Most Relevant Keyword | topic knowledge | PV | NOT STARTED | 5
|  | current issue with some humor | PV | NOT STARTED | 5
|  | write your knowledge | PV | NOT STARTED | 5
|  | blogging will help too | PV | NOT STARTED | 5
7 | Bidding for Keyword | go to GKP | PV | NOT STARTED | 5
|  | select your zone of marketing | PV | NOT STARTED | 5
|  | show u the keywords best for u | PV | NOT STARTED | 5
|  | quote the rate for them | PV | NOT STARTED | 5
8 | Edit Blogs | topic knowledge | PV | NOT STARTED | 5
|  | current issue with some humor | PV | NOT STARTED | 5
|  | write your knowledge | PV | NOT STARTED | 5
9 | Edit Website | topic knowledge | PV | NOT STARTED | 5
|  | current issue with some humor | PV | NOT STARTED | 5
|  | write your knowledge | PV | NOT STARTED | 5
10 | Edit Advertisement and Posts | topic knowledge | PV | NOT STARTED | 5
|  | current issue with some humor | PV | NOT STARTED | 5
|  | write your knowledge | PV | NOT STARTED | 5
|  | type of content flowing | PV | NOT STARTED | 5
11 | Reddit Commenting | choose and set best suitable time for reddit commenting | PV | NOT STARTED | 5
|  | use bought keyword during replying of comments | PV | NOT STARTED | 5
12 | Creating the Best Marginal Utility Function | topic knowledge | PV | NOT STARTED | 5
|  | current issue with some humor | PV | NOT STARTED | 5
|  | give the audience what they are craving for | PV | NOT STARTED | 5
13 | Checking the Brochures and Editing | publishing tools | SS | NOT STARTED | 5
|  | demographics | SS | NOT STARTED | 5
|  | age of audience | SS | NOT STARTED | 5
|  | type of content flowing | SS | NOT STARTED | 5
14 | Increase Traffic on Website | seo | SS | NOT STARTED | 5
|  | blogging | SS | NOT STARTED | 5
|  | posting | SS | NOT STARTED | 5
15 | Show Response through Google Analytics | reviewing | SG | NOT STARTED | 5
|  | showing | SG | NOT STARTED | 5
16 | Show Response through Facebook Analytics (post traffic) | reviewing | SG | NOT STARTED | 5
|  | showing | SG | NOT STARTED | 5
17 | Show Hyperstat (website traffic) | reviewing | SG | NOT STARTED | 5
|  | showing | SG | NOT STARTED | 5
18 | Tying Up |  | SG | NOT STARTED | 5
PV - PRATEEK VASHISHTHA
SG - SHAKTI GOKHRU
SS - SHYAM SINGH

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 45 | 54 | Tasks
2018-10-18 | 36 | 54
2018-10-20 | 27 | 54
2018-10-21 | 18 | 54
2018-10-22 | 9 | 54
2018-10-23 | 0 | 54
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Digital College>
SB4/US1 | Add D-DOS Code in Website | SB4/D1/T1 | code created | PV,SG,SS | NOT STARTED
|  | SB4/D1/T2 | add the code in head file of website code | PV,SG,SS | NOT STARTED
|  | SB4/D1/T3 |  | PV,SG,SS | NOT STARTED
SB4/US2 | Circulate Website Traffic | SB4/D2/T1 | open torr browser | PV,SG,SS | NOT STARTED
|  | SB4/D2/T2 | set the browser in the ip changing platform in every 3 sec | PV,SG,SS | NOT STARTED
|  | SB4/D2/T3 | loop up the auction to visit the website with diff ups | PV,SG,SS | NOT STARTED
|  | SB4/D2/T4 |  | PV,SG,SS | NOT STARTED
|  | SB4/D2/T5 |  | PV,SG,SS | NOT STARTED
SB4/US3 | Maintain the Traffic | SB4/D3/T1 | open torr browser | PV,SG,SS | NOT STARTED
|  | SB4/D3/T2 | set the browser in the ip changing platform in every 3 sec | PV,SG,SS | NOT STARTED
|  | SB4/D3/T3 | loop up the auction to visit the website with diff ups | PV,SG,SS | NOT STARTED
|  | SB4/D3/T4 |  | PV,SG,SS | NOT STARTED
SB4/US4 | Keep on Creation of Post | SB4/D4/T1 | topic knowledge | PV,SG,SS | NOT STARTED
|  | SB4/D4/T2 | current issue with some humor | PV,SG,SS | NOT STARTED
|  | SB4/D4/T3 | write your knowledge | PV,SG,SS | NOT STARTED
|  | SB4/D4/T4 | and create the image | PV,SG,SS | NOT STARTED
|  | SB4/D4/T5 |  | PV,SG,SS | NOT STARTED
SB4/US5 | Make New Posts and Advertisement on Social Media | SB4/D5/T1 | topic knowledge | PV,SG,SS | NOT STARTED
|  | SB4/D5/T2 | current issue with some humor | PV,SG,SS | NOT STARTED
|  | SB4/D5/T3 | write your knowledge | PV,SG,SS | NOT STARTED
|  | SB4/D5/T4 | and create the image | PV,SG,SS | NOT STARTED
SB4/US6 | Make Bid on New Keyword | SB4/D6/T1 |  | PV,SG,SS | NOT STARTED
|  | SB4/D6/T2 |  | PV,SG,SS | NOT STARTED
|  | SB4/D6/T3 |  | PV,SG,SS | NOT STARTED
|  | SB4/D6/T4 |  | PV,SG,SS | NOT STARTED
|  | SB4/D6/T5 |  | PV,SG,SS | NOT STARTED
SB4/US7 | Maintain Website with New Bidding Keywords | SB4/D7/T1 |  | PV,SG,SS | NOT STARTED
|  | SB4/D7/T2 |  | PV,SG,SS | NOT STARTED
|  | SB4/D7/T3 |  | PV,SG,SS | NOT STARTED
|  | SB4/D7/T4 |  | PV,SG,SS | NOT STARTED
|  | SB4/D7/T5 |  | PV,SG,SS | NOT STARTED
SB4/US8 | Make and Post New Blogs | SB4/D8/T1 |  | PV,SG,SS | NOT STARTED
|  | SB4/D8/T2 |  | PV,SG,SS | NOT STARTED
|  | SB4/D8/T3 |  | PV,SG,SS | NOT STARTED
|  | SB4/D8/T4 |  | PV,SG,SS | NOT STARTED
SB4/US9 | Design New Brochures according to need | SB4/D9/T1 |  | PV,SG,SS | NOT STARTED
|  | SB4/D9/T2 |  | PV,SG,SS | NOT STARTED
|  | SB4/D9/T3 |  | PV,SG,SS | NOT STARTED
|  | SB4/D9/T4 |  | PV,SG,SS | NOT STARTED
SB4/US10 | Maintain the Daily Update through Website | SB4/D10/T1 |  | PV,SG,SS | NOT STARTED
|  | SB4/D10/T2 |  | PV,SG,SS | NOT STARTED
|  | SB4/D10/T3 |  | PV,SG,SS | NOT STARTED
|  | SB4/D10/T4 |  | PV,SG,SS | NOT STARTED
PV - PRATEEK VASHISHTHA
SG - SHAKTI GOKHRU
SS - SHYAM SINGH

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Add D-DOS Code in Website | code created | PV,SG,SS | NOT STARTED
|  | add the code in head file of website code | PV,SG,SS | NOT STARTED
|  |  | PV,SG,SS | NOT STARTED
2 | Circulate Website Traffic | open torr browser | PV,SG,SS | NOT STARTED
|  | set the browser in the ip changing platform in every 3 sec | PV,SG,SS | NOT STARTED
|  | loop up the auction to visit the website with diff ups | PV,SG,SS | NOT STARTED
|  |  | PV,SG,SS | NOT STARTED
|  |  | PV,SG,SS | NOT STARTED
3 | Maintain the Traffic | open torr browser | PV,SG,SS | NOT STARTED
|  | set the browser in the ip changing platform in every 3 sec | PV,SG,SS | NOT STARTED
|  | loop up the auction to visit the website with diff ups | PV,SG,SS | NOT STARTED
|  |  | PV,SG,SS | NOT STARTED
4 | Keep on Creation of Post | topic knowledge | PV,SG,SS | NOT STARTED
|  | current issue with some humor | PV,SG,SS | NOT STARTED
|  | write your knowledge | PV,SG,SS | NOT STARTED
|  | and create the image | PV,SG,SS | NOT STARTED
|  |  | PV,SG,SS | NOT STARTED
5 | Make New Posts and Advertisement on Social Media | topic knowledge | PV,SG,SS | NOT STARTED
|  | current issue with some humor | PV,SG,SS | NOT STARTED
|  | write your knowledge | PV,SG,SS | NOT STARTED
|  | and create the image | PV,SG,SS | NOT STARTED
6 | Make Bid on New Keyword |  | PV,SG,SS | NOT STARTED
|  |  | PV,SG,SS | NOT STARTED
|  |  | PV,SG,SS | NOT STARTED
|  |  | PV,SG,SS | NOT STARTED
|  |  | PV,SG,SS | NOT STARTED
7 | Maintain Website with New Bidding Keywords |  | PV,SG,SS | NOT STARTED
|  |  | PV,SG,SS | NOT STARTED
|  |  | PV,SG,SS | NOT STARTED
|  |  | PV,SG,SS | NOT STARTED
|  |  | PV,SG,SS | NOT STARTED
8 | Make and Post New Blogs |  | PV,SG,SS | NOT STARTED
|  |  | PV,SG,SS | NOT STARTED
|  |  | PV,SG,SS | NOT STARTED
|  |  | PV,SG,SS | NOT STARTED
9 | Design New Brochures according to need |  | PV,SG,SS | NOT STARTED
|  |  | PV,SG,SS | NOT STARTED
|  |  | PV,SG,SS | NOT STARTED
|  |  | PV,SG,SS | NOT STARTED
10 | Maintain the Daily Update through Website |  | PV,SG,SS | NOT STARTED
|  |  | PV,SG,SS | NOT STARTED
|  |  | PV,SG,SS | NOT STARTED
|  |  | PV,SG,SS | NOT STARTED
PV - PRATEEK VASHISHTHA
SG - SHAKTI GOKHRU
SS - SHYAM SINGH

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 30 | 30 | Tasks
2019-01-11 | 24 | 30
2019-01-12 | 18 | 30
2019-01-13 | 12 | 30
2019-01-14 | 6 | 30
2019-01-15 | 0 | 30
0
Days